# Vircle Doc Sign: delivery plan

Document 2 of 3 for review. Architecture, data, security, work packages and rollout, second revision 6 Oct 2026

Table of Contents

# 1. Summary

Vircle Doc Sign is built natively inside Halo (decision: option B in the proposal). It signs any document (PDF, Word, image), supports a signing list with an optional signing order, and groups documents into categories. Ready-made packs, starting with Merchant Registration, come as add-ons. Nothing from the OpenSign fork is copied; its behaviour is used as a reference only, so no AGPL obligation arises. It is built in phases behind an operator switch, first for Vircle only.

Second revision (merchant application sample and e-invoice form). The merchant application is filled in parts, over several sittings, from one link, includes the new e-invoice tax details, and exists as variants per merchant group (A, B, C) with different fees and terms. That adds a forms layer (Phase 1B) between the core signing product and the merchant go-live.

| Phase | Result | Effort (one engineer) |
| --- | --- | --- |
| 0 | Decisions, legal read, certificate ordered, real merchant application and terms received | 3 days, overlaps phase 1A |
| 1A | Core signing. Any PDF, Word file or image prepared and sent to a signing list (in order if chosen); a merchant signs on a phone; the sealed PDF is filed; categories and the add-on mechanism | 46 days, about 9 weeks |
| 1B | Forms and merchant groups. The application filled in parts from one link with autosave; conditional fields and uploads; e-invoice tax details; variants per merchant group; the Merchant Registration add-on goes live | 22 days, about 4.5 weeks |
| 2 | Automation, API, webhooks, part-aware reminders, countersign in Halo, share a part, option lists, envelopes, bulk send, add-on updates | 31 days, about 6 weeks |
| 3 | Public registration entry, trusted certificate, verify page, retention, hardening, form without signature | 17 days, about 3.5 weeks |

Merchant go-live is at the end of Phase 1B: about 68 working days, roughly 13.5 weeks. The whole programme is about 119 days (24 weeks) for one engineer; two engineers working in parallel on 1A and 1B bring go-live forward to about 9 weeks. Until 1B is built, an agent can send the application as a document the merchant fills directly on the page (with save and resume), with the tax details as an extra page; nothing sent in the meantime is lost.

These are planning figures. Phase 1 grew from 35 to 46 days after your note on Word files, categories and add-ons, and the signing list: Word conversion service 4 days, categories and add-ons 4, wider field types and the prepare-any-document path 2, signing-order logic 1. (The 35 days were already longer than the 5 to 6 weeks in the earlier proposal, because pricing the whole Halo checklist adds about a week.) Phases can overlap with a second pair of hands.

# 2. What is reused from Halo, and what is new

| Need | Reuse | New |
| --- | --- | --- |
| Tenancy | accounts, account_id plus row-level security | Sign tables |
| Roles | Capability system (capabilities.ts, role defaults, Roles screen) | sign.* permissions |
| Switch and limits | account_platform features and limits, usage meters | flags sign and sign_merchant, limit sign_documents_per_month |
| Files | Private storage with signed URLs, existing storage meter | bucket sign-documents |
| Email | Resend client and per-workspace sender identity | invitation, reminder, completed emails |
| WhatsApp | sendMessageToConversation / template sending helpers | invitation template |
| Contacts | contacts, custom fields, timeline, notifications | Documents tab, events |
| Automation | engine (runAutomationsForTrigger, runStep) | trigger and step |
| Integration | outbound webhooks, /api/v1, API keys and scopes | events and routes |
| Secrets | key ring and ENCRYPTED_COLUMNS | certificate and sensitive fields |
| Audit | audit_log, append-only pattern, file hashes from incidents | sign_events chain |
| Export and deletion | table discovery, storage by prefix | retention exception |
| Rate limits, client IP | rate_limit_hit, trusted-proxy rule | signer endpoints |
| Word to PDF | none | conversion service (container) |
| Custom contact fields | custom_fields | fields installed by an add-on |

New dependencies, to be licence-checked before merge in WP2: pdf-lib (stamping), pdfjs-dist (page rendering in the browser), @signpdf/signpdf with its pdf-lib placeholder and P12 signer (PKCS7 sealing), node-forge (certificate handling), signature_pad (drawn signatures) and a QR library for the certificate page. All are understood to be permissively licensed (MIT, BSD or Apache); this is confirmed per package in WP2 and recorded in the repository. Word conversion uses Gotenberg, an open-source (MIT) service that runs LibreOffice in the background, as a separate container; LibreOffice keeps its own licence and is not modified or linked into Halo.

# 3. Architecture

Sender (Halo UI)                          Signer (public page, no login)
      |                                              |
      v                                              v
 /sign/*  dashboard pages            /sign/[token]   public signing page
 /api/sign/*  (requireCapability)    /api/sign/public/[token]/*  (token auth)
      |                                              |
      +----------- src/lib/sign/*  (shared logic) ---+
           |            |             |            |
        templates    ceremony      pdf engine    notifications
           |            |             |            |
           v            v             v            v
        Postgres (RLS)   Storage (private)   Resend / WhatsApp / automations / webhooks

- Where it runs. Inside the existing Halo container: pages, API routes and the PDF engine. The engine is plain TypeScript with no framework imports, so it can move to its own worker container later if load needs it, without a rewrite.

- Background work. Sealing, reminders and expiry run as leased jobs (the pattern from migration

  - driven by one cron route, /api/sign/jobs-cron, every minute. Sealing is queued, not done in the signer’s request, with at most 2 at once.

- No second database. All state is in Halo’s Postgres. All files are in Halo’s storage.

- One new container. The conversion service (section 6), reachable only from the Halo container.

# 4. Data model

All tables have account_id uuid not null references accounts(id) on delete cascade, row-level security on, and updated_at triggers. Names start sign_. Migrations start at 157.

| Table | Purpose | Key columns |
| --- | --- | --- |
| sign_categories | A document category | key, name, defaults (expiry, reminders, code required, sign in order, consent wording, retention), add-on key (if installed by one), archived |
| sign_addons | Which add-ons a workspace has installed | add-on key, installed version, installed by and when, status |
| sign_templates | A template’s identity | name, description, category, family and variant key (for example Merchant group A), status (draft, active, archived), current version, tags, add-on key and version if it came from one, “customised” flag |
| sign_template_versions | Immutable version of a template | version no., source file path and SHA-256, page count, fields (json), roles (json), defaults (expiry, reminders, order, language, subject, message) |
| sign_documents | One document sent for signing | reference (SGN-2026-000123), title, status, category, template version (nullable), contact, ticket, deal, merge_values, fields_snapshot, sign_in_order flag, locale, expires at, sent at, completed at, original upload (path, type, SHA-256), converted PDF, base file and SHA-256, final file and SHA-256, void reason, created by |
| sign_document_files | Files that belong to a document | kind (source, annex, signer upload, signed, certificate), path, name, size, SHA-256 |
| sign_signers | A person who signs | role key, full name, email, phone, channel, order number (step), invited at, status, token hash, code hash and attempts, viewed, signed and declined times, decline reason, IP, device, locale, consent version |
| sign_answers | Everything entered, in form mode or on the page | document, signer, data field key, value (json) or file, source (signer, sender, contact, colleague), saved at, sensitive flag |
| sign_template_families | A family of variants (Merchant Application) | name, category, form, add-on key |
| sign_forms | An immutable form definition per version | ordered parts, data field keys in each part, text per language |
| sign_data_fields | Definition of each data field | key, labels and help per language, type, options or option list, validation, required rule, show-if rule, contact field it fills, sensitive flag, default per variant |
| sign_contributors (P2) | Colleague links for one part | document, part keys, name, email, token hash, status |
| sign_option_lists (P2) | Shared option lists | name, items with labels per language |
| sign_events | Append-only audit chain | document, signer, type, actor (user, signer, system), detail (json), IP, device, prev_hash, row_hash, time |
| sign_settings | One row per workspace | default expiry, reminder days, default language, consent texts (per language), sender name, logo, retention years, certificate reference |
| sign_certificates | Sealing certificates | name, subject, valid until, encrypted P12 and passphrase, default flag |
| sign_forms (P3) | Public registration forms | slug, fields to contact mapping, template, automation, consent text |

Document status: draft, sent, in_progress, sealing, completed, declined, expired, voided, failed. Allowed moves are enforced by a trigger, not only by the app.

Signer status: pending, sent, viewed, signed, declined.

Signing order. Each signer has an order number; signers sharing a number are one step. With sign_in_order off, every step is invited at once and the numbers are ignored. With it on:

- Only step 1 is invited when the document is sent. Later signers have a link from the start but it opens only a “waiting for {name}” page with no document content.

- When a signer finishes, the server locks the document row, checks whether every signer in the step is done, and if so invites the next step in the same transaction. A unique record per document and step makes the invitation happen once even if two signers finish at the same moment.

- A decline, a void or an expiry stops the chain. Reminders go only to the current step.

- The last step finishing moves the document to sealing. The whole thing is tested with parallel, sequential, mixed and racing cases.

draft -> sent -> in_progress -> sealing -> completed
              \-> declined      \-> failed (retry)
              \-> expired
 any non-final state -> voided

The audit chain. sign_events.row_hash = sha256(prev_hash || canonical row). A database trigger computes it under a per-document lock, and update and delete are blocked, using the same append-only pattern as Halo’s audit log. A function sign_verify_chain(document) recomputes the chain; the Document detail screen shows “Audit trail intact” from it.

Not stored in plain text: link tokens and codes (hashes only); the certificate and its passphrase (encrypted, key ring); fields marked sensitive (encrypted, P2).

# 5. Files and the sealing pipeline

Storage. Private bucket sign-documents, path account-<id>/<document>/<kind>/<name>. Signed-in members can read their own workspace’s objects only through server-made signed links; nobody has insert, update or delete rights from the browser. Only the server writes. The existing storage meter already counts anything under account-<id>/ in any bucket.

Pipeline.

- Freeze (on send). The server writes merge values onto the template PDF, saves it as the base file, records its SHA-256, and snapshots the field definitions into the document. From now on the template can change without affecting this document.

- Each signer. The server validates every value (type, required, pattern, size), stores it, and appends events. The browser only collects input.

- Seal (when the last signer finishes). A queued job loads the base PDF, draws every value and signature image, appends the completion certificate pages (document id, SHA-256 of the content, every signer’s details, times, devices, verification, consent), adds a QR code to the verify page (P3), applies a PKCS7 signature with the workspace’s certificate, saves the final file, records its SHA-256, writes events, marks the document completed and sends the emails.

- Download. Every download re-computes the SHA-256 and compares it with the stored value; a mismatch blocks the download and raises an alert.

- Idempotent. The seal job is keyed by document, so a retry after a crash cannot seal twice.

Certificate. Phase 1 uses an organisational certificate, held encrypted, that signs every sealed file. PDF readers show the signature as intact but not yet “trusted” until Phase 3 replaces it with a certificate from a recognised certificate authority. Procurement takes time, so it is ordered in Phase 0.

# 6. Word conversion and preparing any document

Why a service. A faithful Word to PDF conversion needs a full layout engine. The service is Gotenberg (LibreOffice inside), run as a container beside Halo.

- Network. Halo calls it at a fixed address set by SIGN_CONVERTER_URL. The container has no route to the internet and no published port. Halo’s outbound guard refuses private addresses by design, so the converter client is a separate, trusted client that only ever calls this one configured address; no workspace or user can set it.

- Safety. Uploaded Word files are untrusted. Macros never run during conversion. The container is non-root, read-only except a temporary folder, limited to about 1 GB of memory and one or two conversions at once, with a 60-second limit. The result is checked to be a real PDF, within the page limit, before it is accepted. The Word file is never sent to a signer, only the converted PDF.

- Fidelity. Standard fonts convert closely (Arial, Times New Roman and Courier New are matched by metric-compatible fonts). Fonts the converter does not have are replaced, which can move text. Vircle’s own fonts are added to the converter image. Tracked changes and comments should be cleared before upload (the upload screen says so). The editor always shows the converted pages with “This is exactly what will be signed”, and the sender can replace the file or upload a PDF instead.

- Images. JPG and PNG become one-page PDFs inside Halo, with no converter.

- If the converter is down. Word upload shows “Word conversion is not available right now. Upload a PDF instead.” Everything else keeps working. The Platform console job card shows its health.

- Cost. The image is large (on the order of 1 GB or more) and peak memory while converting is several hundred MB. Both are measured in WP3 and added to the weekly cleanup notes.

Prepare any document. The field editor is one component used three ways: editing a template, preparing a template-based document (values only), and preparing an uploaded document (full placement). From the wizard or from a contact, a sender uploads a file, the editor opens on its pages, and “Save as template” copies the prepared fields into a template at any moment.

# 7. Categories and add-ons

- Categories are plain rows with defaults (section 4). A document’s effective settings are the category’s defaults over the workspace’s, then any choice made on the document itself.

- Add-ons are defined in the code base, versioned, and contain a category, template source files (PDF or Word), custom contact field definitions, wording in the supported languages and, later, an automation recipe and a registration form. They live in src/lib/sign/addons/<key>/.

- Operator switch. Whether a workspace may use an add-on is a platform feature flag (sign_merchant for Merchant Registration), off for new workspaces, on for Vircle.

- Install. A workspace Owner or Admin presses Install. One transaction creates the category, creates the templates as drafts to review, creates any missing contact fields, and records the installed version. It can be repeated safely and never overwrites anything the workspace changed: an edited add-on template is marked “customised” and an update only offers a new version beside it.

- Update (Phase 2). A new add-on version shows “Update available” with a change list.

# 8. Forms in parts, and merchant groups

Data fields and placements. Asking and printing are separate. A data field (key, labels, type, rules) is asked once. A placement puts its value at a place on the PDF; one data field can have many placements, or none (data only). In the editor a placed field is bound to a data field instead of being typed. Merge from the contact (F-06) is just a data field whose first value came from the contact.

The form. A template has a form definition: ordered parts, each a list of data fields. The signer’s page has two modes: form mode (parts, then review and sign) and overlay mode (fields on the page, used by one-off documents). A template can use either.

Rules in one place. Visibility (“show tax percentage only when tax type is SST”), required-if, validation (digits, length, pattern, phone, postcode, file type and size) and part completion are all computed by one shared TypeScript module used by the browser for instant feedback and by the server as the authority. The rule language is a small JSON form (equals, not equals, in, empty, not empty, and, or), so it can be stored, tested and shown in the builder.

Autosave and resume. - The browser sends changed answers in small batches (about every second while typing and when leaving a field). The server validates each value, stores it in sign_answers, and returns what is valid. Answers are never kept only in the browser. - Two tabs or devices: the latest save for a field wins and the other device is told “this answer was changed elsewhere”. Offline changes queue and resend. - The single link plus the code (when on) opens a verified session valid for 12 hours; the overview shows each part as Not started, In progress or Done, computed by the shared module. - Audit: a “sitting” event is written at most once per 5 minutes; “part completed”, “part reopened” and “submitted” are always written. Keystrokes are never logged.

The gate. The sign step is locked in the interface until required parts are done, and the server re-checks the entire answer set when the signature arrives; it never trusts the browser’s idea of which parts are complete.

Printing answers. Placements draw text with automatic shrinking inside their box and wrap multi-line values; a list prints one entry per line or comma separated. If an answer cannot fit even at the smallest size the signer is told which field to shorten before they can sign, and fixed values (fees, terms) are checked for fit when the variant is saved. Uploaded files are stored with their SHA-256, listed in the certificate, and appended to the sealed packet as annexes where required.

Write-back. Each data field can name a contact field. On submission (and, if chosen, per part) the server updates the contact in one transaction through the existing contact update path, writes an audit line with old and new values, and by default only overwrites a value after it was shown to and confirmed by the signer.

Families and variants. - A variant is a normal template carrying a family and a variant key. All variants of a family share one form and one set of data fields, so the tax part and contacts are identical everywhere. - The merchant group is a contact field. The wizard offers the group; from a contact that has one it is preselected; the automation step takes the group as an input. - Commercial values (fees, notice period, settlement, payment channel note) are data fields with each variant’s defaults. They are locked on the merchant’s page and on the sender’s wizard unless the workspace setting “senders may change fees” is on. - Compare shows two variants side by side (fields, values, wording differences). “Copy fields from” matches placements by label so a new group starts from an existing one. - A new version of a variant never changes sent documents; the sealed record names group, variant and version.

Share a part (P2). A colleague link is scoped to chosen part keys, has its own token, shows only those parts, records the colleague’s name and email on each change (source “colleague”), and can never reach the sign step.

# 9. Signer security

- Link: 32 random bytes, only its SHA-256 stored, shown once. Reissuing a link kills the old one.

- Code: 6 digits, hashed, 10 minutes, 5 tries, then locked for 15 minutes; resends are limited.

- Rate limits: per link, per network address and per workspace, using Halo’s shared limiter. The address comes from the trusted-proxy rule already used elsewhere.

- Pages: signing pages are served no-store, with no search indexing, and do not reveal whether a link ever existed (a wrong link and an expired link look different only to the signer who has the right one).

- Files: the document is streamed through a route that checks the link on every request; storage addresses are never handed to the browser.

- Cross-tenant: signer routes use the service role, so they are written to look up by token hash only and to return only that signer’s document. A test asserts that a token never reads another document’s data.

- Signer uploads: type and size checked, stored under the document, scanned by type only (no macros possible in the allowed types).

- Staff access: reading requires sign.view; writes happen only through server routes that call requireCapability; the audit log records administrative changes.

# 10. Where each part touches Halo

| Part | Files and conventions |
| --- | --- |
| Database | supabase/migrations/157_sign_foundation.sql onward, idempotent. CI: lines in supabase/ci/platform-grants.sql; authenticated_ok and bucket entries in verify-guard-catalog.sql; verify-157-sign-*.sql ending in ROLLBACK-OK. |
| Permissions | capabilities.ts (menu.sign, sign.view, sign.send, sign.void, sign.templates, sign.settings, sign.sign), CapabilityKey, capabilities-sql.test.ts, capability-parity.test.ts, role defaults in the migration. |
| Navigation | sidebar.tsx nav item, page-access.ts, settings-sections.ts. |
| Switch and limits | features.ts (sign and sign_merchant in PLATFORM_FEATURES, FEATURE_CAPABILITIES, sign_documents_per_month in PLATFORM_LIMITS), validate.ts, platform-console.tsx, usage.ts (assertCanSendDocument), account_usage() and snapshots. |
| Seed function | account_platform_seed() is recreated in full, carrying incidents, jira, vircle_chat, sign and sign_merchant. |
| Pages | src/app/(dashboard)/sign/... (list, templates, editor, document), public src/app/sign/[token]/page.tsx. |
| API | src/app/api/sign/* (staff, requireCapability), src/app/api/sign/public/[token]/* (token auth, listed in PUBLIC_ROUTES in route-surface.test.ts), src/app/api/v1/sign/* (P2). |
| Conversion | docker-compose.sign.yml (converter service, internal network), SIGN_CONVERTER_URL, converter client in src/lib/sign/convert/, health on the Platform job card. |
| Add-ons | src/lib/sign/addons/merchant/ (manifest, template files, fields, wording), installer route, Settings > Doc Sign > Add-ons. |
| Forms | src/lib/sign/forms/ (rules, validation, completion, printing fit), routes /api/sign/public/[token]/answers and /parts, contact write-back through the existing contact update helper, form builder under (dashboard)/sign/templates/[id]/form. |
| Jobs | /api/sign/jobs-cron through cronRoute, CRON_INTERVALS, Platform job card string, crontab line in docs/automations-and-cron.md. |
| Engine | src/lib/sign/ (pdf/, ceremony/, tokens.ts, events.ts, templates/, notify.ts). |
| Notifications | notification types widened in the migration; email templates beside invitation-email.ts. |
| Automation | AutomationTriggerType, TRIGGER_META, builder, validate.ts, engine.ts, a step in runStep (P2). |
| Webhooks | WEBHOOK_EVENTS entries sign.sent, sign.viewed, sign.completed, sign.declined, sign.expired (P2). |
| Audit | new actions and entity types in src/lib/audit/types.ts and the check constraint. |
| Export and deletion | tables discovered automatically; list sign_events children if needed; the retention exception; teardown has no external registrations. |
| Contacts | merge_contacts() repoint for sign_documents.contact_id; soft-delete behaviour reviewed. |
| Language and guide | Sign namespace in four languages, content/help/sign/*, neutral-wording test, CHANGELOG.md, version bump 0.76.0. |
| Public registration address | the signer page and verify page added to registered-urls.ts only if a provider needs it (no). |

# 11. Work packages

## Phase 1A: core signing (46 days)

| WP | Work | Days |
| --- | --- | --- |
| 1 | Foundation: tables (including categories, add-ons, signing steps), RLS, grants, bucket, append-only chain, permissions, switches, quota scaffolding, audit actions, export and deletion rules, verify scripts, parity tests | 5 |
| 2 | PDF engine: merge render, stamping of every field type, certificate pages, PKCS7 sealing, hashes, verification, golden test files checked with an independent verifier | 7 |
| 3 | Conversion service: container and compose file, converter client, size, time and page checks, preview and error messages, fonts, image-to-PDF, tests with a set of real Word files | 4 |
| 4 | Editor: viewer, field placement and properties for all field types, roles, merge keys, versions, library, preview, prepare-any-document path, save as template | 10 |
| 5 | Send and sign: wizard, signing list with full name, email and order, order logic, invitations (email, WhatsApp), tokens and codes, signing page on mobile, signatures, uploads, decline, waiting and end states, seal job | 10 |
| 6 | Management: list with category filter, detail, audit view, contact tab, notifications, downloads, void, remind, resend, change recipient | 4 |
| 7 | Categories and add-ons: category settings, add-on catalogue and installer, operator switch | 4 |
| 8 | Settings, platform and finish: Settings, Platform console, four-language strings, User Guide, documentation, device testing | 2 |

## Phase 1B: forms and merchant groups (22 days)

| WP | Work | Days |
| --- | --- | --- |
| 9 | Data fields and form definition: tables, field types, shared rule and validation module, option lists seed, binding placements to data fields in the editor | 6 |
| 10 | Form-mode signing: overview with parts, part screens, autosave and resume, progress, locked review and sign, mobile, languages | 6 |
| 11 | Sender side: form builder, progress view, reminders naming unfinished parts, extend expiry, write-back to contact fields | 4 |
| 12 | Families and merchant groups: variants, group picker, auto-choice from the contact, commercial values with defaults, compare and copy | 3 |
| 13 | Merchant Registration content: the real application with the e-invoice part, groups A, B and C, wording in English and Bahasa Melayu, tests on the real files | 3 |

## Phase 2 (31 days)

| WP | Work | Days |
| --- | --- | --- |
| 14 | Automation trigger and step (with the merchant group as an input), webhooks, recipe “Merchant onboarding” | 4 |
| 15 | Public API /api/v1/sign, scopes, API docs | 3 |
| 16 | Part-aware reminders and expiry job, countersign inside Halo | 5 |
| 17 | Envelopes (several documents, one sitting) | 4 |
| 18 | Bulk send, CSV export, zip download | 3 |
| 19 | Share a part (colleague links) | 3 |
| 20 | Option lists in Settings and the MSIC code picker | 3 |
| 21 | Sensitive-field encryption and masking, template test mode, ticket and deal attach, replace file, add-on updates | 6 |

## Phase 3 (17 days)

| WP | Work | Days |
| --- | --- | --- |
| 22 | Public registration entry and anti-abuse | 3 |
| 23 | CA-issued certificate rollout, verify page | 5 |
| 24 | Retention rules and the deletion exception | 3 |
| 25 | Form without signature (standalone e-invoice details) | 2 |
| 26 | Load test, security review, fixes | 4 |

# 12. Testing

- Unit tests (Vitest): tokens and codes, state moves, merge rendering, field validation, hash chain, sealing steps, permissions, and the signing-order logic (parallel, sequential, mixed steps, two signers finishing at once, decline mid-chain, change recipient mid-chain).

- Forms tests: the rule module (visibility, required-if, validation for every type), part completion, autosave with two devices, resume after the code, the server re-check at signing, answers that overflow a box, conditional uploads, write-back with old and new values, and variant selection.

- Conversion tests: a set of real Word files (tables, images, headers, tracked changes, Malay text, large and corrupt files) converted and compared page by page; oversized and macro-laden files rejected or neutralised.

- Database checks: verify-157 and later scripts for row-level security, chain integrity, blocked updates, cascade, quota; run in CI against an empty database and against production (rolled back) before each migration is applied.

- PDF proof: sealed golden files verified by an independent tool (for example pdfsig or an OpenSSL check) in CI where available and by hand in common PDF readers before each release.

- Security tests: token guessing and reuse, replay after reissue, cross-workspace reads, oversized and wrong-type uploads, rate limits.

- Device matrix before the pilot: iPhone Safari, Android Chrome, one low-end Android, a desktop browser, each in English and Bahasa Melayu; keyboard-only and screen-reader pass.

- Pilot: three real merchants, with the owner watching events live.

# 13. Rollout

- Build behind the sign switch, off for everyone.

- Switch on for the Vircle workspace and use test documents.

- Pilot with three merchants once Phase 1B is done (about 68 working days from the go-ahead). Fix what they hit.

- Open to all Vircle users, then enable Phase 2 automation.

- Decide whether to offer to customers; that is a switch plus pricing, not new code.

Deployment. One new container (the converter), a migration, a redeploy of Halo, and one crontab line. The VPS size is not recorded anywhere, so measure memory and CPU of one seal job in WP2 and of one conversion in WP3 and report; if either needs headroom, the engine moves to a small worker container on the same host (the gateway pattern).

# 14. Risks

| Risk | Effect | Handling |
| --- | --- | --- |
| Legal weight of the signature for merchant contracts in Malaysia | A contract could be challenged | Phase 0 legal read; decide if a licensed certificate is required at launch; consent and audit trail from day one |
| Certificate procurement is slow | Trusted signature arrives late | Order in Phase 0; Phase 1 uses an organisational certificate |
| PDF stamping uses CPU and memory | Slows Halo | Queue, 2 at a time, measure in WP2, worker container as fallback |
| Word files convert imperfectly (fonts, layout) | The signed document differs from what the author saw | Preview with “this is exactly what will be signed”, Vircle fonts added, PDF recommended for exact layout |
| Long forms are abandoned halfway | Merchants never finish | Autosave, one link that resumes anywhere, reminders that name the unfinished parts, share-a-part for colleagues |
| Conditional rules grow complicated | Hard to review and test | Small rule language, one shared module, previews in the builder, tests for every rule |
| Answers longer than the boxes on the printed form | Text cut off in a signed contract | Auto-shrink, wrapping, a clear message before signing, fixed values checked when saved |
| Converter handles untrusted files | Attack surface | Isolated container with no internet, resource limits, result validation, never served back |
| Phone browsers differ (drawing, upload, zoom) | Merchants cannot sign | Device matrix; typed signature as an alternative |
| WhatsApp template approval | Invitations by WhatsApp delayed | Email works from day one; submit the template in Phase 0 |
| Retention versus workspace deletion | Either contracts lost or deletion promise broken | Decision needed now (question 6 in the feature document) |
| Scope growth (editor features) | Delays | Phase gates; “Later” list in document 1 |
| Library licences or maintenance | Rework | Checked in WP2 and recorded |

# 15. Decisions needed before Phase 1 starts

- The assumptions in the feature document, section 1.

- First template: the actual agreement and its fields (feature document, questions 2 and 3).

- Countersigner and order (question 4).

- Retention period and the deletion exception (question 6).

- Certificate: who orders it, and whether a CA-issued one is mandatory at launch.

- VPS memory and CPU figures, or permission to measure them. Also: the merchant group definitions and the option lists (feature document, questions 9 to 15).

- The merchant agreement as Word and PDF, with its fonts, so conversion can be tested on the real file.

- Brand name on customer-facing wording while the module is Vircle-only (the help pages for it are owner-only so Halo’s neutral-wording test still passes).